MOODMATE Mental Wellness Platform 99.9% Completeness Implementation Plan July 2026 • Version 1.0 Current: ~62% → Target: 99.9%

# 1. Executive Summary

MoodMate is a full-stack mental wellness platform built on Spring Boot 3.5 / Java 21 (backend) and React Native / Expo SDK 54 (Android). The core student wellness loop — mood check-in, AI chat, journal, habits, sleep, breathing, games, community, and gamification — is production-quality and feature-complete. The remaining ~38% gap is concentrated in deployment infrastructure, payment checkout, counsellor profile editing, and real-time messaging configuration. This plan closes every gap in five structured phases totalling approximately 16 developer-days of focused work.

| Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 |
| --- | --- | --- | --- | --- |
| Deployment | Feature Gaps | Polish | Hardening | App Store |
| ~3 days | ~5 days | ~4 days | ~2 days | ~2 days |

# 2. Phase-by-Phase Plan

| P1 | Production Deployment Infrastructure | ~3 days • BLOCKING |
| --- | --- | --- |

Everything else in this plan is moot until the backend has a real, internet-accessible URL and the frontend knows how to reach it. This phase must be completed before any user testing or APK distribution.

| # | Task & Detail | Effort | Files / Endpoints |
| --- | --- | --- | --- |
| 1.1 | Deploy backend to Render Create a Web Service on render.com pointing at the GitHub repo. Set build command: mvn package -DskipTests. Start command: java -jar target/*.jar. Free tier is sufficient for beta. | 3 hrs | render.com dashboard + GitHub |
| 1.2 | Migrate database to Supabase PostgreSQL Create a Supabase project. Copy the PostgreSQL connection string (Transaction mode, port 6543). Set DB_URL, DB_USERNAME, DB_PASSWORD on Render. Flyway will auto-run all V1–V15 migrations on first boot. | 2 hrs | supabase.com + Render env vars |
| 1.3 | Set all required environment variables on Render JWT_SECRET (32+ random chars), GROQ_API_KEY, MAIL_HOST/PORT/USERNAME/PASSWORD, PAYSTACK_SECRET_KEY, PAYSTACK_PUBLIC_KEY, PAYSTACK_CALLBACK_URL (moodmate://payment-callback), CORS_ALLOWED_ORIGINS (*). Remove dev defaults. | 1 hr | Render → Environment → Add Env Var |
| 1.4 | Replace hardcoded IP in frontend with env-based config Rename src/config.ts → read from app.config.js extra field. Add app.config.js exporting BACKEND_BASE_URL from process.env.EXPO_PUBLIC_API_URL. Create .env.development (local IP) and .env.production (Render URL). Add .env* to .gitignore. | 2 hrs | src/config.ts, app.config.js, .env.* |
| 1.5 | Add eas.json with development and production profiles Create eas.json with three profiles: development (Expo Go), preview (internal APK, env=staging), and production (store APK, env=production). Set EXPO_PUBLIC_API_URL in each profile's env block. | 1 hr | eas.json (new file) |
| 1.6 | Configure UPLOADS_PATH to persistent storage Avatar uploads use ./uploads by default — ephemeral on Render. Option A: Set UPLOADS_PATH to a Render Disk mount (/var/data/uploads). Option B: Migrate to Supabase Storage (recommended for scale): add supabase-java SDK, create avatars bucket, update UserController.uploadAvatar to call supabase.storage().from("avatars").upload(). | 3 hrs | UserController.java, application.yml |

| P2 | Critical Feature Gaps | ~4 days • USER-FACING |
| --- | --- | --- |

Features that real users will immediately notice are broken or missing. Each item here represents a user journey that either fails completely or shows incorrect information.

| # | Task & Detail | Effort | Files / Endpoints |
| --- | --- | --- | --- |
| 2.1 | Counsellor profile editing — backend endpoint Add PUT /api/support/counsellor/profile endpoint to SupportController (or new CounsellorProfileController). Accepts: title, bio, specialties, available (boolean). Updates counsellors table for the authenticated user's userId. Return updated CounsellorView. | 2 hrs | SupportController.java, CounsellorRepository.java |
| 2.2 | Counsellor profile editing — frontend screen Replace all hardcoded data in CounsellorProfileScreen.tsx: load real profile via GET /api/support/counsellor/me (or existing counsellor endpoint). Add "Edit Profile" modal/sheet with TextInputs for title, bio, specialties, availability toggle. On save, call PUT /api/support/counsellor/profile and refresh. | 4 hrs | src/screens/counsellor/CounsellorProfileScreen.tsx |
| 2.3 | Fix CounsellorSignupScreen messaging Remove all "pending approval" copy. New messaging: "Have your email added to the approved list by the MoodMate admin first, then log in with your credentials using the Counsellor option." Remove or repurpose the counsellor-request form submission since whitelist is now the gate. | 1 hr | src/screens/counsellor/CounsellorSignupScreen.tsx |
| 2.4 | Wire Paystack checkout on Pro screen In ProScreen.tsx and ShopScreen.tsx, replace "coming soon" with: (1) call POST /api/payments/subscribe or /api/payments/leaf-packs to get a Paystack authorization_url. (2) Open URL via WebBrowser.openAuthSessionAsync(url, "moodmate://payment-callback"). (3) Handle the deep link in App.tsx with Linking.addEventListener — call GET /api/payments/verify to confirm and refresh auth store. | 5 hrs | ProScreen.tsx, ShopScreen.tsx, App.tsx, api/payments.ts |
| 2.5 | Set up Supabase real-time for in-app messaging Create a Supabase project (free tier). In Dashboard → SQL Editor, run: CREATE TABLE messages (...) and enable replication (ALTER PUBLICATION supabase_realtime ADD TABLE messages). Replace placeholder credentials in src/lib/supabase.ts with EXPO_PUBLIC_SUPABASE_URL and EXPO_PUBLIC_SUPABASE_ANON_KEY. Add both to .env files. | 3 hrs | src/lib/supabase.ts, Supabase dashboard |
| 2.6 | AI paywall gate on frontend Instead of a raw API error toast when the free daily limit is hit, intercept 402 responses in AiChatScreen.tsx and navigate to ProScreen (or show an in-line upgrade card). Makes the monetisation loop intentional. | 2 hrs | src/screens/ai/AiChatScreen.tsx, api/client.ts |
| 2.7 | Align Pro checkout with industry patterns (Headspace / Calm model) Redesign ProScreen.tsx with: (1) Plan comparison table — Free vs Pro columns with checkmarks per feature. (2) Prominent annual toggle showing monthly cost and "Save 45%" badge. (3) 7-day free trial CTA as the primary button. (4) Trust signals — secure payment badge, cancel-any-time note, testimonial snippet. (5) "Restore Purchases" button (required by Play Store). Mirror the Headspace/Calm pattern of leading with value, not price. | 3 hrs | src/screens/payments/ProScreen.tsx, src/components/PlanComparisonCard.tsx (new) |
| 2.8 | Add Google Play Billing as primary IAP channel Google Play requires digital goods to go through their billing system (or face app removal). Install expo-iap (maintained fork of react-native-iap). Define two SKUs in Play Console: moodmate.pro.monthly and moodmate.pro.annual. On purchase success, call POST /api/payments/verify-play with the purchaseToken; backend validates with Google Play Developer API and upgrades the user's plan. Keep Paystack as the web/promo fallback path. | 6 hrs | package.json, src/api/payments.ts, PaymentsController.java, GooglePlayVerifier.java (new) |

| P3 | Feature Polish | ~3 days • QUALITY |
| --- | --- | --- |

These items close the gap between a working app and a good app — features that exist but are rough around the edges, missing small pieces, or inconsistent with the rest of the experience.

| # | Task & Detail | Effort | Files / Endpoints |
| --- | --- | --- | --- |
| 3.1 | Appointment push notifications Add a Spring @Scheduled job (AppointmentReminderJob.java) that runs hourly. Finds appointments starting in the next 60 minutes with status CONFIRMED. Calls PushNotificationService.sendToUser() for both the student and counsellor. Add to the existing push package alongside StreakReminderJob. | 3 hrs | push/AppointmentReminderJob.java (new) |
| 3.2 | Counsellor availability slot management Add a counsellor_availability table (V16 migration): counsellor_id, day_of_week (0–6), start_time, end_time. New GET /api/support/counsellor/{id}/slots endpoint returns available time slots for a given date. SupportScreen.tsx replaces hardcoded slot array with a fetch from this endpoint. | 5 hrs | V16__availability.sql, SupportController.java, SupportScreen.tsx |
| 3.3 | Add typed API modules for Habits and Sleep Create src/api/habits.ts and src/api/sleep.ts mirroring the pattern of other API files. Move all inline fetch calls from HabitTrackerScreen.tsx and SleepTrackerScreen.tsx into these modules. Improves testability and catches type errors at compile time. | 2 hrs | src/api/habits.ts (new), src/api/sleep.ts (new) |
| 3.4 | Avatar delete endpoint + frontend wiring Add DELETE /api/users/avatar to UserController.java: clears avatarUrl on the user row and deletes the file from storage. In EditProfileScreen.tsx, wire the "Remove photo" button to call this endpoint and refresh the auth store user object. | 2 hrs | UserController.java, EditProfileScreen.tsx |
| 3.5 | EAS environment profiles (dev / staging / prod) In eas.json, add EXPO_PUBLIC_API_URL per profile. Add staging profile pointing at a Render preview service (or use --branch flag). Document the three build commands: eas build --profile development, --profile preview, --profile production. | 1 hr | eas.json, .env.staging (new) |
| 3.6 | Appointment email notifications When a counsellor confirms or completes an appointment (AppointmentService.java), send an email to the student via JavaMailSender (already configured for OTP). Template: "Your appointment with [Counsellor] on [Date] at [Time] has been confirmed." | 2 hrs | AppointmentService.java, EmailService.java |
| 3.7 | New game: Thought Untangler (CBT card-swipe) A CBT-grounded swipe game. Cards fall showing common negative automatic thoughts (e.g. "I always mess everything up", "Nobody cares"). Player swipes LEFT to reframe ("This one time went badly — that is not always") or RIGHT to release ("This thought does not serve me"). After 10 cards: score screen shows cognitive distortion patterns detected (all-or-nothing, catastrophising, mind-reading) with a short psychoeducation blurb. Earns 15 XP per session. Backend: thought_cards table (V17 migration), GET /api/games/thought-cards returns shuffled set. Session result POST /api/games/thought-untangler/result logs score + distortion patterns for future AI insights. | 6 hrs | src/screens/games/ThoughtUntanglerScreen.tsx (new), V17__thought_cards.sql (new), GamesController.java |
| 3.8 | New game: Zen Garden (mindfulness sand-drawing) A no-lose, open-ended mindfulness drawing game. User draws in a virtual sand tray using their finger — strokes render as raked sand lines with a subtle particle trail. Three rake widths, three sand colours. A soft ambient tone plays (reuses existing music player service). Session auto-ends at 5 minutes or when user taps "Done". Completion awards 10 XP and counts as a mindfulness minute toward the daily goal. No backend state needed beyond the existing XP award endpoint (POST /api/gamification/award-xp). Add entry card in ExploreScreen games section. | 5 hrs | src/screens/games/ZenGardenScreen.tsx (new), src/components/SandCanvas.tsx (new), ExploreScreen.tsx |

| P4 | Security Hardening & Performance | ~2 days • NON-NEGOTIABLE |
| --- | --- | --- |

Items that do not affect visible features but will cause incidents in production if skipped. These must be done before any real user data enters the system.

| # | Task & Detail | Effort | Files / Endpoints |
| --- | --- | --- | --- |
| 4.1 | Rotate JWT_SECRET to a production value Generate a 64-character random hex string (openssl rand -hex 32). Set as JWT_SECRET on Render. Never commit to source. All existing sessions will be invalidated — acceptable pre-launch. | 30 min | Render env vars, start.bat (for local dev) |
| 4.2 | Lock down CORS to production origin Set CORS_ALLOWED_ORIGINS on Render to the Expo app's origin (or * is acceptable for a mobile-only API since there are no cookies/credentials). More importantly, ensure Spring Security's CSRF is disabled for stateless JWT and not accidentally re-enabled. | 1 hr | application.yml, SecurityConfig.java |
| 4.3 | Add React Native error boundary Create src/components/ErrorBoundary.tsx (class component, required for React error boundaries). Wrap the NavigationContainer in App.tsx. On error: show a friendly "Something went wrong" screen with a Retry button. Log error to console (or future Sentry integration). | 2 hrs | src/components/ErrorBoundary.tsx (new), App.tsx |
| 4.4 | Secure start.bat for local development Confirm start.bat is in .gitignore. Add a .gitignore entry check in README. Rotate Gmail App Password if it was ever committed. Add start.bat.example with placeholder values for onboarding new developers. | 30 min | start.bat, .gitignore, start.bat.example (new) |
| 4.5 | Optimise FlatList-heavy screens Screens with long lists (CommunityScreen, AdminDashboard whitelist, CounsellorAppointmentsScreen) should use keyExtractor, getItemLayout where possible, and removeClippedSubviews={true}. Wrap heavy child components in React.memo to prevent re-renders on parent state changes. | 2 hrs | CommunityScreen.tsx, AdminDashboardScreen.tsx |
| 4.6 | Add basic accessibility labels Add accessibilityLabel and accessibilityRole to all interactive Pressable/TouchableOpacity elements that currently have only icon or emoji children. Priority: tab bar items, action buttons in counsellor cards, modal close buttons, streak shield button. | 3 hrs | MainTabs.tsx, CounsellorDashboardScreen.tsx, HomeScreen.tsx |

| P5 | App Store Preparation & Final QA | ~2 days • LAUNCH GATE |
| --- | --- | --- |

The last mile: everything needed to submit to Google Play (and optionally Apple App Store) and pass review. Also includes the final end-to-end QA pass across all user roles.

| # | Task & Detail | Effort | Files / Endpoints |
| --- | --- | --- | --- |
| 5.1 | Finalise app icon and splash screen Ensure assets/icon.png (1024×1024), assets/adaptive-icon.png (foreground layer, 1024×1024), and assets/splash.png (1284×2778 for safe zone) are the final branded versions. Run npx expo-optimize to compress. Verify adaptive icon looks correct on round/square launchers. | 2 hrs | assets/, app.json |
| 5.2 | Add privacy policy URL and required metadata Add privacyPolicyUrl to app.json extra field. Create a simple Privacy Policy page (GitHub Pages or Notion public page is sufficient). Add Terms of Service link. Required by both Google Play and Apple App Store. | 2 hrs | app.json, external privacy policy URL |
| 5.3 | Produce production APK via EAS Run: eas build --platform android --profile production. Download the signed .aab (Android App Bundle). Test the bundle on a physical device via: npx uri-scheme open moodmate:// --android. Confirm deep links, push notifications, and payments work outside Expo Go. | 3 hrs | EAS dashboard, physical Android device |
| 5.4 | Google Play Store listing Create an app in Google Play Console. Upload the .aab. Set content rating (pass the questionnaire: mental wellness, no violence, no data sharing with third parties). Write store description, short description. Upload at least 4 screenshots per required screen size. Set content rating to Everyone / PEGI 3. | 4 hrs | play.google.com/console |
| 5.5 | End-to-end QA checklist — all user roles Student: signup → onboarding → mood check-in → AI chat (free + paid limit) → journal → habit → sleep → community → booking → messaging. Counsellor: whitelist add → signup → login (auto-promote) → profile edit → confirm appointment → messaging. Admin: setup → whitelist → stats dashboard. Guest: explore → prompt to register. | 4 hrs | All screens, physical device + emulator |

# 3. Completeness Tracker

| Feature Area | Now | Target | Phase | Progress |
| --- | --- | --- | --- | --- |
| Student wellness loop | 95% | 99% | P3 / P4 | ██████████ 95% |
| Auth & security | 90% | 99% | P1 / P4 | █████████░ 90% |
| Admin panel | 90% | 99% | P1 | █████████░ 90% |
| Push notifications | 85% | 99% | P3 | █████████░ 85% |
| In-app messaging | 65% | 98% | P2 | ███████░░░ 65% |
| Counsellor dashboard | 70% | 99% | P2 / P3 | ███████░░░ 70% |
| Counsellor profile editing | 15% | 99% | P2 | ██░░░░░░░░ 15% |
| Appointment booking | 75% | 95% | P3 | ████████░░ 75% |
| Payments / Paystack | 45% | 98% | P2 | █████░░░░░ 45% |
| Production config (frontend) | 20% | 99% | P1 | ██░░░░░░░░ 20% |
| Production config (backend) | 60% | 99% | P1 / P4 | ██████░░░░ 60% |
| File / avatar storage | 50% | 98% | P1 | █████░░░░░ 50% |
| Error handling / boundaries | 70% | 98% | P4 | ███████░░░ 70% |
| Accessibility | 30% | 85% | P4 | ███░░░░░░░ 30% |
| App store readiness | 10% | 99% | P5 | █░░░░░░░░░ 10% |
| End-to-end QA | 20% | 99% | P5 | ██░░░░░░░░ 20% |
| OVERALL | ~62% | 99.9% | P1–P5 | ~16 developer-days total |

# 4. Execution Order & Dependencies

Some tasks in later phases can begin in parallel with earlier ones. The dependency chain is:

| 1.1 Render deploy | → | 1.2 Database → 1.3 Env vars → 1.4 Frontend config → All API calls work in prod |
| --- | --- | --- |
| 1.4 Frontend config | → | 1.5 eas.json → 5.3 Production APK |
| 1.6 File storage | → | 3.4 Avatar delete (both need storage layer decided) |
| 2.1 Counsellor endpoint | → | 2.2 Counsellor profile screen (backend must exist first) |
| 2.5 Supabase setup | → | Real-time messaging works (fallback polling works independently) |
| 2.4 Paystack checkout | → | 2.6 AI paywall gate (both part of the monetisation flow) |
| 3.2 Availability slots | → | 3.1 Appointment reminders (slots must exist to know what to remind) |
| P1–P4 complete | → | 5.5 End-to-end QA → 5.4 Play Store submission |

# 5. What Is Already Production-Quality

These features need no further work before launch. They are stable, security-hardened, and consistent across the codebase:

- Core student wellness loop: Mood check-in with trigger tags, daily goals, streak system with shield, milestone push notifications, tree gamification with XP and leaf economy.

- AI Chat & Insights: Groq-powered chat with voice input and image support; daily usage gating for free tier; AI-generated mood insights. Freemium enforcement is server-side.

- Journal system: Templates (Daily Reflection, Exam Stress, Gratitude Jar, Goals & Wins), full CRUD, rich entry cards.

- Habit & Sleep Trackers: Full backend V11/V12 migrations, toggle endpoints, frontend screens with stats. Both features are end-to-end.

- Quabble-inspired features: Worry Box, Safe Place visualisation, and Proud Dandelion wins screen are all fully implemented with animations.

- Gamification & Store: XP bar, leaf balance, streak shield purchase, skin system. Backend wallet transactions are auditable via the LeafTransaction table.

- Community & Crisis: Community posts with delete, crisis keyword detection on check-in submissions, open alert count in AdminDashboard, counsellor crisis badge.

- Counsellor whitelist system: V15 migration, entity, repository, admin endpoints (GET/POST/DELETE), auto-promotion on login, counsellor profile row creation, all with race-condition handling and proper error codes.

- Push notification infrastructure: Expo Push Notification Service integration, token registration on login/logout, 8 PM streak reminder job, milestone push at days 3/7/14/30.

- Auth & security hardening: OTP brute-force protection, rate limiting on auth endpoints, password complexity, magic-byte avatar validation, JWT expiry, ClientAbortException suppression.

- Music player: Multi-track with favourites, single-player enforcement, Brown Noise / ADHD Focus tracks, premium Ionicons controls.

# 6. Competitor Checkout Analysis

Tasks 2.7 and 2.8 are grounded in how the leading mental wellness apps monetise. The patterns below were drawn from Headspace, Calm, Wysa, Finch, and Sanvello and adapted to MoodMate's student-focused context.

| Feature | Headspace | Calm | Wysa | Finch / Sanvello | MoodMate Plan |
| --- | --- | --- | --- | --- | --- |
| Freemium tier | Yes — core content free | Yes — limited tracks | Yes — 150+ free exercises | Yes — full free tier | Yes — 5 AI msgs/day, all games free |
| Free trial | 7-day free trial | 7-day free trial | No trial, always free | 14-day free trial | 7-day Pro trial (Task 2.7) |
| Monthly price | $12.99 / mo | $14.99 / mo | $4.99 / mo | $5.99–$8.99 / mo | TBD — suggest ~$5.99 |
| Annual saving | ~55% off monthly | ~50% off monthly | ~60% off monthly | ~50% off monthly | Show "Save 45%" badge prominently |
| Lifetime option | $399.99 one-time | Yes — $399.99 | No | No | Consider after launch |
| IAP platform | Google Play Billing + App Store IAP | Google Play + App Store | Google Play + App Store | Google Play + App Store | expo-iap (Task 2.8) + Paystack web fallback |
| Plan comparison screen | Yes — table format | Yes — card format | Minimal | Feature list | Table + animated toggle (Task 2.7) |
| Restore purchases | Yes | Yes | Yes | Yes | Required — add to ProScreen (Task 2.7) |
| HSA/FSA payment | Yes (US only) | No | No | No | Out of scope for v1 |
| Games / activities | Mindfulness exercises | Breathing + sleep sounds | 150+ CBT/DBT exercises | Self-care quests | BubblePop + Breathing + Thought Untangler + Zen Garden |

## Key Checkout Design Principles (from competitor analysis)

- Lead with value, not price: Headspace and Calm both show the feature list before any pricing. Users who see what they are paying for convert at 2–3x the rate of those who see a price-first screen.

- Annual plan as the default selection: All top apps default to the annual toggle with the monthly equivalent shown ("just $4.16/mo"). Monthly is available but de-emphasised. This directly increases LTV.

- Free trial with no credit card required: Wysa and Finch prove that a permanently-free tier can drive retention without a trial. MoodMate's hybrid — free tier + 7-day Pro trial — captures both audiences.

- Google Play Billing is non-negotiable: Google Play Store policy requires digital subscription goods to use Play Billing. Paystack alone will result in app removal. expo-iap wraps the native billing API and is the correct solution for Expo apps.

- Restore Purchases: Required by both Google Play and Apple App Store review guidelines. Omitting it is a rejection reason. It must appear on the paywall screen.

## New Games: Design Rationale

| Game | Therapeutic Basis | Inspiration | MoodMate Fit |
| --- | --- | --- | --- |
| Thought Untangler | Cognitive Behavioural Therapy (CBT) — specifically cognitive restructuring and identification of cognitive distortions. Clinically validated for anxiety and depression. | Wysa's 150+ CBT exercises, Woebot's thought-challenging conversations, SuperBetter's "Bad Guys" mechanic for defeating negative patterns. | Extends the existing CBT Thought Diary screen with a game loop. Data (distortion patterns identified) feeds into AI Insights. Rewards XP, reinforcing the streak + gamification system. |
| Zen Garden | Mindfulness-based stress reduction (MBSR) — specifically sensory grounding and present-moment focus. The act of slow, deliberate drawing activates the parasympathetic nervous system. | Calm's soundscapes, Headspace's "mini meditations," and the physical zen garden tradition used in occupational therapy and school counselling settings. | No win/lose state removes performance anxiety — rare in the existing game set. Reuses the music player service. Counts as mindfulness minutes toward the daily goal. Appeals to students who prefer creativity over challenge. |

Completing this plan takes MoodMate from a strong local prototype to a shippable, monetisable, production-grade mental wellness app. ~16 developer-days • 5 phases • 99.9% complete